IBMS — POS Compliance Gap Analysis & Sprint Plan

Scope: per-branch POS / CRM permit filings — three branches

Prepared: 27 April 2026

# Reclassification Note

Earlier drafts of this document framed IBMS as a Computerized Accounting System (CAS) candidate. On reconsideration, IBMS is more accurately classified as a Point-of-Sale system: it issues invoices and records payments but does NOT maintain books of accounts (no General Journal, no General Ledger, no posting workflow). The correct BIR accreditation is therefore a per-branch POS / CRM Permit to Use (PTU), filed at each branch's RDO, not a CAS Acknowledgment Certificate at the Head Office.

This reclassification simplifies the filing materially (lighter documentary set, faster turnaround, per-branch scope) but does NOT change the engineering work required of IBMS. The EOPT invoice rules (sequential serials, audit trail, mandatory fields, 10-year retention) apply to POS systems as fully as they do to CAS.

# Executive Summary

IBMS is functionally complete for POS and order management. To file POS permits and go live across the three branches, the gaps below must be closed. Estimated effort: roughly 2 weeks of focused development plus 1 week of UAT — same as the earlier estimate, since the engineering changes are not driven by the choice of permit type.

# Gap Table

P0 = blocker for filing. P1 = required for go-live. P2 = recommended hardening.

| # | Requirement | Current State | Fix | Pri |
| --- | --- | --- | --- | --- |
| 1 | Sales Invoice as principal sales document (EOPT / RR 7-2024) | POS prints a 'Receipt' HTML with no BIR header fields | Rename to Sales Invoice; server-render PDF with all Section 237 fields | P0 |
| 2 | Sequential, non-resettable serial per branch | Uses generic order_number sequence | Per-branch PostgreSQL sequence; format LM-BR<code>-<00000001>; no reset | P0 |
| 3 | Mandatory fields: seller TIN incl. branch code, VAT status, customer TIN ≥ PHP 1k | Absent from printReceipt() | Extend DB + UI + print template; pull seller info from branch config | P0 |
| 4 | VAT breakdown (VATable / Exempt / Zero-Rated / VAT Amount) | No tax columns on orders / order_items | Add columns; compute server-side; mirror onto invoice + line items | P0 |
| 5 | SC / PWD discount handling (20% off + VAT-exempt + ID capture) | Plain discount column | Add discount_type enum + ID capture; tax computation handles SC/PWD correctly (already done in vat.ts) | P0 |
| 6 | Immutable audit trail on sales-side records | No audit_trail table | Add audit_trail + Drizzle middleware + Postgres triggers (DONE in Sprint 1) | P0 |
| 7 | Collection Receipt for subsequent payments | Not distinct from invoice | Add collection_receipts table + issuance flow (DONE in Sprint 1 schema) | P0 |
| 8 | Void / reversal — no hard delete of posted invoices | Orders can be deleted via schema | Add posted flag + Postgres trigger blocking DELETE/UPDATE on posted (DONE in SQL post-migration) | P0 |
| 9 | 10-year electronic retention | Neon PITR is only 30 days | Nightly encrypted pg_dump → Cloudflare R2 with 10y retention + object lock | P0 |
| 10 | Z-Reading per branch / end-of-day close | Not implemented | Add register_sessions + Z-Reading generator; block next day until previous closed | P0 |
| 11 | PTU + MIN injection on every invoice | Not printed | After BIR issues PTU + MIN per branch, inject into invoice template | P0 (post-PTU) |
| 12 | Monthly Sales Summary + Collection Summary (for accountant) | Not implemented | Build monthly summary PDFs for the accountant to post into the loose-leaf books | P1 |
| 13 | Maker-checker on pricing edits | Single admin | Approval workflow for services and admin tables | P1 |
| 14 | Data Privacy Act compliance | None | Separate legal track (deferred) | P1 |
| 15 | Restoration drill log | None | Quarterly drill artifact in /ops/drills/ | P2 |

# Sprint Plan

## Sprint 1 — Schema + Invoice Layer (DONE on feat/bir-cas-sprint-1 branch)

- sales_invoices, sales_invoice_items, collection_receipts tables.

- Per-branch invoice / CR sequences via Postgres functions issue_invoice_number() and issue_cr_number().

- audit_trail table + Drizzle middleware (auditedInsert, auditedUpdate, withAudit, postSalesInvoice, voidSalesInvoice).

- VAT / Percentage Tax computation library in @aunt-sallys/shared/tax — 14 tests, all passing.

- Postgres triggers: append-only audit_trail; posted invoices immutable; collection_receipts no-delete; per-line items locked when parent invoice is posted.

- branches schema extended with branch_code, rdo, registered_address, bir_registered_on for invoice serial generation and receipt-header rendering.

## Sprint 2 — POS, Voids, Z-Reading, Archival (NEXT)

- Rewrite printReceipt() in apps/pos/src/pages/OrderDetail.tsx → call /api/v1/invoices/:id/print returning a server-rendered PDF.

- Implement Collection Receipt issuance flow when payment is recorded against an invoice in a later session.

- Implement Void: posted invoices cannot be deleted; void issues paired reversal with cross-reference.

- register_sessions table + Z-Reading generator; block new sales if previous day not closed.

- Monthly Sales Summary + Collection Summary report generators for the accountant.

- Nightly encrypted pg_dump → Cloudflare R2 with 10-year retention and object-lock.

## UAT (Week 3)

- Parallel run at Arton West for one week: IBMS invoices side-by-side with hand receipts; daily reconciliation.

- Tag the release as v1.0.0-pos. Lock the branch.

- Run the first restoration drill; file the Drill Report in /ops/drills/.

## Filing (Week 3 end → Week 4)

- Fill remaining placeholders in the per-branch packages (contact number, notarization city, AIBOS address, HQ address).

- Notarize each Sworn Statement.

- File at RDO 039 (Xavierville + Arton West together) and at RDO 043 (Tiendesitas).

- Once each PTU + MIN is issued, inject into IBMS and redeploy.